## Log for Final Project
Date: | What I worked on: |  | Duration: | Notes:
(hours)
2021-03-29 | Topic Research and Decision |  | 1.5 | Worked on it before class. Attended open lab for a second opinion from the professor and made several changes
2021-03-30 | Project Proposal Creation and Submission |  | 0.5 | Described target audience, potential color schemes, and specific topics that would be included
2021-04-09 | Sitemap |  | 0.5 | Used Draw.io to create a heirarchial site map.
2021-04-09 | Wireframe |  | 1 | Created a wireframe for the home page, Form page, and page that will hold media
2021-04-11 | Finished and Submited Wireframe |  | 1 | Finished the wire frame and submitted it
2021-04-13 | Reworked Wireframe |  | 2 | Altered the Wireframe to fit a two-coloumn layout format based on the project instructions
2021-04-19 | Research on Censorship in America and Germany |  | 2 | Sources: FCC, https://www.fsk.de/?seitid=1287&tid=480,
2021-04-20 | Reworked the Forms Wireframe to now be an information review/suggestion area instead of idea submission only |  | 0.5 | After class this day and group discussions I decided to change the use of the form on my web site
2021-04-20 | Research on Censorship in Brazil and North Korea |  | 2 | gov.br, https://www.jstor.org/stable/1225545
2021-04-21 | Research on Censorship in UAE, South Africa, and Australia |  | 2 | https://freedomhouse.org/country/united-arab-emirates/freedom-net/2019, https://www.researchgate.net/publication/307824902_Public_Servant_or_Censor_The_South_African_Broadcasting_Corporation_in_the_Era_of_Political_Television_Advertising | https://www.aph.gov.au/About_Parliament/Parliamentary_Departments/Parliamentary_Library/Publications_Archive/archive/censorshipebrief
2021-04-22 | Topic Changed After reviewing Professor Kelleher's comments. Reworked site map |  | 1
2021-04-24 | Created Wireframe. Started researching general information about North Korea censorship |  | 2
2021-04-27 | Researched information about Internet and News Censorship |  | 3
2021-05-01 | Researched information about TV and Film Censorship |  | 2
2021-05-05 | Began coding navigation and research information for tv , internet, and, news |  | 2
2021-05-08 | Coded home page and form |  | 2.5
2021-05-09 | Coded CSS for external and embedded |  | 3
2021-05-10 | Added photos and coded references |  | 2
2021-05-11 | Coded the jquery for the fotorama on the home page |  | 5
2021-05-12 | Uploaded the website to tiger web and submitted assignment |  | 2
|  | Total Hours: | 37.5